Initial Project Planning Template

| Date | 29 September 2026 |
| --- | --- |
| Team ID | 6ab4ce760fc666a751b52130 |
| Project Name | AI StudyBuddy |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members | Sprint Start Date | Sprint End Date (Planned) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Authentication | USN-1 | As a user, I can register for the application by entering my name, email, and password, so that I get a secure account with JWT tokens. | 3 | High | Ayisha H T, Ashwitha V | 01-Sep-2026 | 07-Sep-2026 |
| Sprint-1 |  | USN-2 | As a user, I can log in with my email and password, so that I receive JWT access and refresh tokens for authenticated API access. | 2 | High |  |  |  |
| Sprint-1 |  | USN-3 | As a user, I can refresh my expired access token using the refresh token, so that I don't need to log in again. | 1 | High |  |  |  |
| Sprint-1 |  | USN-4 | As a user, I can log out, so that my session is ended and tokens are discarded. | 1 | Medium |  |  |  |
| Sprint-2 | Study Material Management | USN-5 | As a student, I can upload a study material file (.txt, .md, .pdf), so that the content is extracted and stored for AI processing. | 3 | High | Sahira Safrin M, Sujatha S | 08-Sep-2026 | 14-Sep-2026 |
| Sprint-2 |  | USN-6 | As a student, I can view a list of all my uploaded materials, so that I can manage my study resources. | 2 | High |  |  |  |
| Sprint-2 |  | USN-7 | As a student, I can view the full details of a single material including all AI-generated content. | 1 | Medium |  |  |  |
| Sprint-2 |  | USN-8 | As a student, I can delete a material I no longer need. | 1 | Medium |  |  |  |
| Sprint-3 | AI Content Generation | USN-9 | As a student, I can generate an AI summary of my uploaded material, so that I get concise bullet-point notes. | 3 | High | Ayisha H T, Sahira Safrin M | 15-Sep-2026 | 21-Sep-2026 |
| Sprint-3 |  | USN-10 | As a student, I can generate AI flashcards from my material, so that I get Q&A cards for quick revision. | 3 | High |  |  |  |
| Sprint-3 |  | USN-11 | As a student, I can generate an AI MCQ quiz from my material, so that I can self-assess my understanding. | 3 | High |  |  |  |
| Sprint-3 |  | USN-12 | As a student, I can generate a personalized AI study plan specifying my goal, hours per day, and number of days. | 3 | High |  |  |  |
| Sprint-4 | Admin & Testing | USN-13 | As an admin, I can view a list of all registered users, so that I can manage the platform. | 2 | Medium | Ashwitha V, Sujatha S | 22-Sep-2026 | 28-Sep-2026 |
| Sprint-4 |  | USN-14 | As an admin, I can delete a user and all their materials from the platform. | 2 | Medium |  |  |  |
| Sprint-4 |  | USN-15 | As an admin, I can view platform statistics (total users and materials count). | 1 | Medium |  |  |  |
| Sprint-4 |  | USN-16 | As a developer, I can test all API endpoints via Postman and document the results. | 2 | High | All Members |  |  |

Sprint Summary (1 Mark)

Total story points and team allocation per sprint.

| Sprint | Epic | Total Story Points | Duration | Team |
| --- | --- | --- | --- | --- |
| Sprint-1 | User Authentication | 7 | 01–07 Sep 2026 | Ayisha H T, Ashwitha V |
| Sprint-2 | Study Material Management | 7 | 08–14 Sep 2026 | Sahira Safrin M, Sujatha S |
| Sprint-3 | AI Content Generation | 12 | 15–21 Sep 2026 | Ayisha H T, Sahira Safrin M |
| Sprint-4 | Admin & Testing | 7 | 22–28 Sep 2026 | Ashwitha V, Sujatha S + All Members |